## Sheet1
IPD - Activity Log Book
Sr. No. | Student SAPID | Student Name | Supervisor | Date | Weekly progress |  | Target for next week
[5 empty] | Individual Contribution | Work done in this week
1 | 60004190058 | Kanaad Deshpande | Aniket Kore | 2022-02-24 | Built Recommendation System | Recommender System built and API Finalized | Create and Integrate API endpoints for List View of Recipes
2 | 60004190057 | Junaid Girkar |  |  | Built Recommendation System
3 | 60004190053 | Jayesh Kavedia |  |  | Finalized Edamam Recipe API
4 | 60004190055 | Jigar Shah |  |  | Finalized Edamam Recipe API
1 | 60004190058 | Kanaad Deshpande | Aniket Kore | 2022-03-10 | Created API Endpoints for List View of Recipes | Created and Integrated API endpoints for List View of Recipes | Create and Integrate API endpoints for Detailed View of Recipes
2 | 60004190057 | Junaid Girkar |  |  | Created API Endpoints for List View of Recipes
3 | 60004190053 | Jayesh Kavedia |  |  | Integrated API Endpoints for List View of Recipes
4 | 60004190055 | Jigar Shah |  |  | Integrated API Endpoints for List View of Recipes
1 | 60004190058 | Kanaad Deshpande | Aniket Kore | 2022-03-24 | Created API Endpoints for Detailed View of Recipes | Created and Integrated API endpoints for Detailed View of Recipes | Create and Integrate API endpoints for Filter Page of App
2 | 60004190057 | Junaid Girkar |  |  | Created API Endpoints for Detailed View of Recipes
3 | 60004190053 | Jayesh Kavedia |  |  | Integrated API Endpoints for Detailed View of Recipes
4 | 60004190055 | Jigar Shah |  |  | Integrated API Endpoints for Detailed View of Recipes
1 | 60004190058 | Kanaad Deshpande | Aniket Kore | 2022-04-07 | Created API Endpoints for Filter Page of App | Created and Integrated API endpoints for Filter Page of App | Improvizing GUI and codebase for review meet.
2 | 60004190057 | Junaid Girkar |  |  | Created API Endpoints for Filter Page of App
3 | 60004190053 | Jayesh Kavedia |  |  | Integrated API Endpoints for Filter Page of App
4 | 60004190055 | Jigar Shah |  |  | Integrated API Endpoints for Filter Page of App
1 | 60004190058 | Kanaad Deshpande | Aniket Kore | 2022-05-05 | Improved Recommendation System | Worked on Code Refinement and Recommendation System | Create and Integrate API endpoints for Wishlist of Recipes
2 | 60004190057 | Junaid Girkar |  |  | Improved Recommendation System
3 | 60004190053 | Jayesh Kavedia |  |  | Worked on code refinement to improve speed of app
4 | 60004190055 | Jigar Shah |  |  | Worked on code refinement to improve speed of app
1 | 60004190058 | Kanaad Deshpande | Aniket Kore | 2022-05-19 | Created API endpoints for Wishlist | Created and Integrated API endpoints for Wishlist of Recipes | IPD Review Meet
2 | 60004190057 | Junaid Girkar |  |  | Created API endpoints for Wishlist
3 | 60004190053 | Jayesh Kavedia |  |  | Integrated API endpoints for Wishlist
4 | 60004190055 | Jigar Shah |  |  | Integrated API endpoints for Wishlist