## Sheet1
IPD - Activity Log Book
Sr. No. | Student SAPID | Student Name | Supervisor | Date | Weekly progress |  | Target for next week
[5 empty] | Individual Contribution | Work done in this week
1 | 60004190058 | Kanaad Deshpande | Aniket Kore | 2021-09-23 | ERD Creation and Database Models Created | ERD Creation and Optimization of Login and Signup Pages | Creating and deploying the survey form as well as creating Home Page for the app
2 | 60004190057 | Junaid Girkar |  |  | ERD Creation and Database Models Created
3 | 60004190053 | Jayesh Kavedia |  |  | Optimized Login and Signup Page Design
4 | 60004190055 | Jigar Shah |  |  | Optimized Login and Signup Page Design
1 | 60004190058 | Kanaad Deshpande | Aniket Kore | 2021-09-30 | Designed the Survey Form for data collection. | Deployed Survey Form and Created Home Page | Studying how to write technical papers
2 | 60004190057 | Junaid Girkar |  |  | Designed the Survey Form for data collection.
3 | 60004190053 | Jayesh Kavedia |  |  | Developed Home Page and Side Bar
4 | 60004190055 | Jigar Shah |  |  | Developed Home Page and Side Bar
1 | 60004190058 | Kanaad Deshpande | Aniket Kore | 2021-10-07 | Learnt how to write research paper through session conducted. | Learnt about writing technical papers | Finding API's for data and creating Profile Page
2 | 60004190057 | Junaid Girkar |  |  | Learnt how to write research paper through session conducted.
3 | 60004190053 | Jayesh Kavedia |  |  | Learnt how to write research paper through session conducted.
4 | 60004190055 | Jigar Shah |  |  | Learnt how to write research paper through session conducted.
1 | 60004190058 | Kanaad Deshpande | Aniket Kore | 2021-10-14 | Researched for existing API's to get Recipe Data | Research about available API's and created Profile related screens | Finalizing API and creating List View Recipe Screen
2 | 60004190057 | Junaid Girkar |  |  | Researched for existing API's to get Recipe Data
3 | 60004190053 | Jayesh Kavedia |  |  | Developed Profile Page and Profile Filling Screen
4 | 60004190055 | Jigar Shah |  |  | Developed Profile Page and Profile Filling Screen
1 | 60004190058 | Kanaad Deshpande | Aniket Kore | 2021-10-28 | Researched for existing API's to get Recipe Data | Finalized Spoonacular API and created List View of Recipes | Creation of API endpoints and integrating them.
2 | 60004190057 | Junaid Girkar |  |  | Researched for existing API's to get Recipe Data
3 | 60004190053 | Jayesh Kavedia |  |  | Developed Search Page and List View of Recipes
4 | 60004190055 | Jigar Shah |  |  | Developed Search Page and List View of Recipes
1 | 60004190058 | Kanaad Deshpande | Aniket Kore | 2021-11-11 | Created API endpoints and API Integration | API endpoints creation and integration and created individual recipe page | IPD Review Meet
2 | 60004190057 | Junaid Girkar |  |  | Created API endpoints and API Integration
3 | 60004190053 | Jayesh Kavedia |  |  | Developed Individual Recipe Page and API Integration
4 | 60004190055 | Jigar Shah |  |  | Developed Individual Recipe Page and API Integration
1 | 60004190058 | Kanaad Deshpande | Aniket Kore | 2021-11-18 | Updated the Technical Paper as Suggested during review meet | Updation of Technical Paper as suggested | Finding an alternative to querying an external API
2 | 60004190057 | Junaid Girkar |  |  | Updated the Technical Paper as Suggested during review meet
3 | 60004190053 | Jayesh Kavedia |  |  | Updated the Technical Paper as Suggested during review meet
4 | 60004190055 | Jigar Shah |  |  | Updated the Technical Paper as Suggested during review meet
1 | 60004190058 | Kanaad Deshpande | Aniket Kore | 2021-11-25 | Researched about switching to Web Scraping instead of using API to fetch data | Researched about Web Scraping | Making improvements in the current app
2 | 60004190057 | Junaid Girkar |  |  | Researched about switching to Web Scraping instead of using API to fetch data
3 | 60004190053 | Jayesh Kavedia |  |  | Researched about switching to Web Scraping instead of using API to fetch data
4 | 60004190055 | Jigar Shah |  |  | Researched about switching to Web Scraping instead of using API to fetch data
1 | 60004190058 | Kanaad Deshpande | Aniket Kore | 2021-12-02 | Created further API endpoints | Improving the app and researching for further functionalities
2 | 60004190057 | Junaid Girkar |  |  | Created further API endpoints
3 | 60004190053 | Jayesh Kavedia |  |  | Studied the Fuzzy Search Algorithm
4 | 60004190055 | Jigar Shah |  |  | Studied the Fuzzy Search Algorithm
1 | 60004190058 | Kanaad Deshpande | Aniket Kore | 2021-12-09 | studied Recommender System | Recommender System | Research Paper
2 | 60004190057 | Junaid Girkar |  |  | studied Recommender System
3 | 60004190053 | Jayesh Kavedia |  |  | studied Recommender System
4 | 60004190055 | Jigar Shah |  |  | studied Recommender System
1 | 60004190058 | Kanaad Deshpande | Aniket Kore | 2021-12-23 | Hands on overleaf,latex,IEEE format | Research Paper | Backend optimisation
2 | 60004190057 | Junaid Girkar |  |  | Hands on overleaf,latex,IEEE format
3 | 60004190053 | Jayesh Kavedia |  |  | Hands on overleaf,latex,IEEE format
4 | 60004190055 | Jigar Shah |  |  | Hands on overleaf,latex,IEEE format
1 | 60004190058 | Kanaad Deshpande | Aniket Kore | 2021-12-30 | Worked on Backend optimisation | Backend Optimisation | Backend Improvements
2 | 60004190057 | Junaid Girkar |  |  | Worked on Backend optimisation
3 | 60004190053 | Jayesh Kavedia |  |  | Tried Implementing Frontend state management
4 | 60004190055 | Jigar Shah |  |  | Tried Implementing Frontend state management
1 | 60004190058 | Kanaad Deshpande | Aniket Kore | 2022-01-06 | Made the DB design efficient | Backend Improvements | Research Paper changes
2 | 60004190057 | Junaid Girkar |  |  | Made the DB design efficient
3 | 60004190053 | Jayesh Kavedia |  |  | Looked for 3rd Party API'S
4 | 60004190055 | Jigar Shah |  |  | Looked for 3rd Party API'S
1 | 60004190058 | Kanaad Deshpande | Aniket Kore | 2022-01-13 | Worked on changes recommended by Mentor | Research Paper changes | ML Model
2 | 60004190057 | Junaid Girkar |  |  | Worked on changes recommended by Mentor
3 | 60004190053 | Jayesh Kavedia |  |  | Worked on changes recommended by Mentor
4 | 60004190055 | Jigar Shah |  |  | Worked on changes recommended by Mentor
1 | 60004190058 | Kanaad Deshpande | Aniket Kore | 2022-01-27 | Researched on Suitable ML Model | ML Model
2 | 60004190057 | Junaid Girkar |  |  | Researched on Suitable ML Model
3 | 60004190053 | Jayesh Kavedia |  |  | Researched on Suitable ML Model
4 | 60004190055 | Jigar Shah |  |  | Researched on Suitable ML Model